## Sheet1
Team BackLog
Task Name | Assignee | Task status | Expected Time to finish | Actual time to finish
Distribute all tasks | Peter | Done | 1 hrs. | 1 hrs.
ECUAL Driver | Peter | Done | 8 hrs. | 10 hrs.
MCAL Driver | Nadeen & Mario | Done | 4 hrs. | 4 hrs.
Common Driver | Peter | Done | 1/2 hrs. | 1/2 hrs.
Simulation design | Mario | Done | 2 hrs. | 2 hrs.
App architecture | All the team | Done | 3 hrs. | 4 hrs.
App Coding | Peter | Done | 5 hrs. | 5 hrs.
Integration | All the team | Done | 4 hrs. | 4 hrs.
Simulation testing | All the team | Done | 1 hrs. | 2 hrs.
Documentation | Nadeen | Done | 4 hrs. | 4 hrs.
Code Indentation | Nadeen & Mario | Done | 3 hrs. | 4 hrs.
Test Protcol Sheet | Mario | Done | 1 hrs. | 1 hrs.